## Slide 1: NSF delivery playbook
NSF Quantum Algorithms Challenge (NOIS3-085) · The Challenge Journey tools applied to this task order
Internal · Working draft · October 2026

## Slide 2: How this edition relates to the template
1
The template stays generic
The Challenge Journey client deck and playbook are unchanged and reusable for any client.
2
Same framework, same tools
This edition applies the six phases and the ten tools to NOIS3-085; nothing new is invented for NSF alone.
3
Every claim traces to a source
Each NSF-specific statement cites an RFTP section, our proposal (v6, Sep 9, 2026) or a public source.
4
Client-facing and internal stay separate
The NSF client deck carries no contractor branding; internal scoring and risks live only here.
5
Update as decisions land
Each NSF or collaborator decision updates one content file; both decks rebuild from it.

## Slide 3: Traceability: every RFTP requirement lands in a phase, with our committed response and status
Phase | RFTP requirements | Our proposal commitment (v6) | Status, Oct 2026
1 Commit | §1.2–1.3 goals; COMPETES and CHIPS authority; $1M Phase 1 purse | Kickoff in award week; pre-competition launch report Part 1 within 7 days | Done
2 Frame | §2.1.1.1 problem analysis and decomposition; challenge statement | Problem statement anchored in industry constraints; scoring dimensions separated | Open: use-case scope
3 Design | §2.1.1.2 rules, terms and conditions; §2.1.6.1 participation agreement; §2.1.5 judging | Rules and agreement drafted in the first 4 weeks; NSF review; judges calibrated | Open: prize structure, criteria
4 Mobilize | §2.1.2 splash page, website, Q&A; §2.1.4 outreach, EPSCoR, webinars; §2.1.1.6 registrant analysis | Outreach to ~280 organizations; monthly registrant-quality reports; launch in early Dec | Splash page and QWC done
5 Select | §2.1.5 judging; §2.1.6.2 eligibility verification; §3.1 solutions by May 20, 2027 | April judging; up to 40 × $25K paid with documented verification | Upcoming: Apr–May 2027
6 Adopt | §2.1.4 collaborator coordination; Phase 2 status webinar; §4.3 close-out; §2.1.8 records | Pairing logistics; status webinar; close-out package from live data | Upcoming: mid-2027–2029
Sources: RFTP NOIS3-085; NOIS3-085 proposal portal response v6 (Sep 9, 2026). Award assumed Sep 16, 2026 per the RFTP Q&A.

## Slide 4: NSF gates: dated decision points to keep the December launch and the May 20 delivery
Gate | Must be true | Decides | Target date
2 Problem approved | Use-case scope decided; collaborator problem areas in hand or a fallback agreed; success criteria measurable | NSF | Late Oct 2026
3 Design signed off | Prize structure chosen against pairing capacity; criteria and weights set; rules and agreement through NSF review; USA.gov posting ready | NSF (with CoECI) | Late Nov 2026
4 Participation check | Registrants on pace by segment and EPSCoR reach; likely high-quality submitters identified monthly | Our team + NSF | Monthly, Jan–Mar 2027
5 Awards approved | Scores reconciled; winners verified (eligibility, DCL 26-022, ethics); NSF concurrence | NSF | Early May 2027
6 Phase 2 go | Pairings agreed with pre-qualified partners; Phase 2 prize and payer defined | NSF + collaborators | Jun–Jul 2027
Dates follow the proposed schedule and RFTP §3.1. The Gate 4 thresholds should be set once the first monthly registrant report is in.

## Slide 5: Tool 1 applied · Readiness: 29 of 40, so proceed, with three dimensions sitting exactly at the threshold
Dimension | Score | Evidence | Action
Executive sponsor | 5 | NSF TIP; Project Triad and Quantum+X are top-level priorities | Keep sponsor at gates 3 and 5
Problem owner ★ | 3 | NSF owns the program; ownership of each use case with the ~8 companies is unclear | Name a contact per company (ask 1–2)
Funding | 3 | Phase 1 purse funded; Phase 2 purse and payer undetermined | Decision before Phase 1 winners
Legal and IP | 4 | COMPETES and CHIPS authority; IP stays with participants; DCL 26-022 certification | FAQ on research security
Absorptive capacity ★ | 3 | Depends on each company's capacity to pilot with teams | Collect pairing capacity (ask 1)
Adoption pathway ★ | 4 | Phase 2 pairing and pilots designed in | Make the pairing path explicit in the rules
Cultural openness | 4 | Industry co-design is built into Quantum+X | —
Measurement | 3 | RFTP metrics are activity-level; no Phase 2/3 outcome metrics yet | Propose outcome KPIs
Internal working assessment for discussion; do not share with the client. Decision rule from the template: proceed at 28+ with no ★ item below 3.

## Slide 6: Tool 3 applied · Challenge fit: 56 of 70, a strong candidate, held back by measurability and outsider access
Criterion | Weight | Score | Note
Important and widely recognized | ×2 | 5 | Algorithm gap is a recognized national priority
Solution not obvious or purchasable ★ | ×2 | 5 | No off-the-shelf quantum advantage for these use cases
Outsiders could contribute | ×2 | 3 | Quantum expertise is a barrier; domain experts help through teaming
Success measurable and judgeable ★ | ×2 | 3 | Paper Phase 1: credibility rests on benchmarks against classical baselines
Statable without confidential context | ×1 | 4 | Depends on how anonymized the collaborator briefs are
IP and data shareable | ×1 | 4 | IP stays with participants; data depends on collaborators
Owner and adoption path ★ | ×2 | 4 | Phase 2 pairing; per-company ownership to confirm
Solvable at reasonable cost | ×1 | 4 | $25K fits a proposal-stage entry; benchmarks add effort
Challenge beats alternatives | ×1 | 4 | Reaches beyond NSF's grantee base; complements Quantum+X funding tracks
Total |  | 56 / 70 | 
Internal working assessment. The two weakest items point to two design actions: a benchmark-credibility criterion, and explicit teaming support between quantum researchers and domain experts.

## Slide 7: Tool 10 applied · Landing-zone plan: the gaps to close before launch
Question | What we know | Gap and owner
Who adopts the result? | Pre-qualified industry partners in Phase 2 | Named contact per company: NSF
Through which route? | Pairing event, joint design, ~6-month pilot, ~9-month monitoring | Defined in RFTP
What budget, when? | Phase 2 prize undetermined; payer undetermined | NSF decision before Phase 1 winners
Do IP and data terms allow it? | IP remains with participants; companies negotiate directly | Guidance for partners on terms: NSF and counsel
What do winners get beyond cash? | Industry pairing; partner data, compute or hardware (to confirm) | Collaborator offers: ask 1
Success at 12, 24, 36 months? | Not yet defined beyond RFTP §4.3 reporting | Propose outcome KPIs: our team
Who holds the network after? | Records relinquished to NSF; database kept one year past performance | RFTP §2.1.5.5, §2.1.8

## Slide 8: Tool 7 applied · Purse: options within $1M, with judging load and pairing capacity as the tests
Option | Structure | Teams entering Phase 2 | Per collaborator (~8) | Verification load by May 20
A · RFTP baseline | 40 × $25,000 | Up to 40 | ~5 | 40 winner verifications and payments
B · Tiered | 20 × $25,000 + 10 × $50,000 | Up to 30 | ~4 | 30; tier line needs reconciled scores
C · Fewer, larger | 20 × $50,000 | Up to 20 | ~2–3 | 20
$2M modification | e.g., 40 × $50,000 | Up to 40 | ~5 | 40; same process, scales unchanged
Practitioner notes
The RFTP invites a better alternative structure; our proposal priced the baseline. Any change goes through NSF before the rules are drafted, not after.
Price is unaffected: the purse is a pass-through at $1M whichever split is chosen.
If collaborators report low pairing capacity, Option A still works if NSF accepts that not every Phase 1 winner enters Phase 2. Say that explicitly in the rules.
RFTP NOIS3-085 §1.3; proposal v6 §5.2.6 (purse is a pass-through with no indirects or fee).

## Slide 9: NSF risk register: the eleven risks most likely to hurt this challenge
Risk | Early warning | Mitigation | Owner
Pairing capacity below winner count | Collaborators can't name team counts | Size winner count to capacity; state pairing limits in rules | NSF
Use cases too vague (or too narrow) | Briefs not in by mid-Nov | Brief template; fallback to sector-level framing | NSF + us
Unverifiable quantum-advantage claims | Submissions lack classical baselines | Evidence-credibility criterion; baseline guidance in rules | Us
Entry burden of NSF-format documents | Registrants drop off at submission | SciENcv guide, office hours, early reminders | Us
Industry judge conflicts | Judge ties to teams or future pairings | Attestations; recusal rule agreed up front | NSF + us
Thin EPSCoR participation | Low registrations from EPSCoR states | State EPSCoR offices; targeted webinars | Us
Holiday-season launch | Slow December sign-ups | Plan a January relaunch push | Us
Research security confusion (DCL 26-022) | Repeated questions in the Q&A forum | Plain-language FAQ reviewed by NSF | NSF + us
Media review delays | Assets waiting on two-week review | Review calendar set in October | Us
Phase 2 prize undefined | Winners unsure what comes next | NSF decision before winners are announced | NSF
40 verifications by May 20 | Judging slips past April | Verify eligibility on arrival; payment process ready | Us

## Slide 10: KPIs: RFTP reporting metrics plus the outcome metrics we propose to NSF
Level | Required by RFTP §4.3.9 | Proposed additions
Activity | Webinar attendees; registered participants; active participants; unique solvers; submissions; countries | Share from EPSCoR jurisdictions; share new to NSF funding; mix by segment (researcher, startup, lab, domain expert, student)
Output | Winners and award amounts; solution records with TRL and taxonomy ID | Share of submissions with credible classical baselines; spread of judge scores
Efficiency | Contractor–government meeting hours | Cost per qualified submission; days from close to award
Outcome | — | Pairings formed; pilots launched; pilots meeting success criteria; follow-on funding or contracts at 12 and 24 months
Capability | Lessons learned; close-out meeting | Reusable rules and brief templates for later Quantum+X tracks; network handed to NSF
Countries is required by the RFTP but participation is U.S.-only; report states and EPSCoR jurisdictions alongside it.

## Slide 11: Next week's session with NSF and the industry collaborators: agenda and facilitator moves
90-min | 60-min | Segment | Facilitator moves | Deck slides
0–10 | 0–5 | Introductions and goals | Each collaborator: one sentence on the problem they'd most like solved | 1–2
10–20 | 5–12 | The landing-zone idea | Land the core point: Phase 1 is built backward from Phase 2 | 3–5
20–30 | 12–17 | Where we are and the timeline | Confirm the December launch; flag the November rules deadline | 4, 6
30–50 | 17–32 | Use cases and the brief | Walk the one-page brief; get a yes or no from each company on writing one | 7
50–65 | 32–42 | Pairing capacity and prize structure | Ask each company for a team count; test options A, B and C | 8
65–80 | 42–52 | Judging and conflicts | Agree the recusal principle; ask for judge nominations | 9
80–90 | 52–60 | Asks, decisions, next 90 days | Confirm a named contact and a date for each ask | 13–15
Hold in reserve: slides 10–12 (mobilize, eligibility, adopt) for questions; send the deck afterward with the asks table as the cover note.

## Slide 12: Question bank for the session
For each collaborator
Which problem would you most want a quantum team working on?
What would a measurable win over your classical method look like?
How many Phase 2 teams could you work with, and with what data or compute?
Who on your team owns a pilot?
For NSF
Open sectors or anchored problem areas?
Is there appetite for a tiered or fewer-larger prize?
Can the rules state a purse that may increase?
When will the Phase 2 prize and payer be settled?
For everyone
What should a judge do if they may later partner with a team?
How should the challenge treat claims of quantum advantage?
What would make this a model for later Quantum+X tracks?

## Slide 13: Open items to confirm before the deck goes out
Item | Why it matters | Status
Official competition name | The deck uses the RFTP title as a placeholder | Confirm
Names of the ~8 collaborating companies | Not in the RFTP; the deck avoids naming them | Confirm with NSF
Phase 2 timing | Deck timeline infers design, pilot and monitoring dates | Indicative
Project Triad details | Taken from press coverage; nsf.gov was not reachable for verification | Verify on nsf.gov
Splash page and QWC handout | Reported done; deck states it | Confirmed by team
Media review | The deck is a client product, and may need NSF review before external sharing | Check with COR