## Slide 1: From reach to a submitted application
SESSION 1 · §3 AND §13 OUTREACH TO SUBMISSIONS
Each stage loses people for a different reason. Name the lever for each drop before launch.
5A / 10
Reached
Engaged
Applications started
Deadline week
Submitted
085 ESTIMATE
Set from plan
No 045 rate yet
240–300 or 540–670
Track % complete
130–160 target
045 PHASE I ACTUAL
Not recorded
557 site sessions, 97 interest forms (May 26)
172 at 4 PM on deadline day; not de-duplicated
10% of starts finished a week out
93 submitted; a third on the last day
CONVERTS TO NEXT
Set from your data
No 045 rate yet
54% or 24%
A third land on the last day
96% eligible (045)
WHY PEOPLE DROP
Wrong audience, or the message misses the segment
Interest without a reason to act now
A registration form or long application adds a step
Teams stall on hard sections and run out of time
Platform strain and late uploads on deadline day
LEVER · OWNER
Named target list; partners qualified · Marketing, checked by PM QA (WF 15)
Info session, office hours, matchmaking; capture contacts · Marketing + APM
Personal nudges to high-likelihood starters · APM
Reminders tiered by progress; help desk staffed · APM
Load test; backup path; deadline-day cover · APM
THE NUMBER THAT DECIDES IT
Started to submitted. 54% is the 045 upper bound from records; 24% applies if 390 starts is right. Confirm with the de-duplicated CoLab export.
ASK THE CLIENT
Which agency channels will amplify, and can we contact past entrants? Does a registration form sit before the application?
Notes: Extends slide 5. Read left to right: each column is a stage; rows give the 085 estimate, the 045 Phase I actual, the conversion to the next stage, why people drop, and the lever and owner. High-likelihood applicants: anyone who attended a session, emailed a question or started early. 045 had 10% of starts finished a week out and a third of submissions on the last day, so mid-window progress predicts only part of the pool. Reached and engaged have no 045 conversion data; set them from campaign data and test in the first two weeks (Workflow 15, worksheet A10). Sources: 045 TRDNT weekly syncs May 26 and July 7; Emmanuel Moges emails July 15 to 17; CIMIT (Santosh Savaliya) on dashboard duplicates.

## Slide 2: From submitted to selected, with a record at every cut
SESSION 3 · §8, §9 AND §10 SUBMISSIONS TO SELECTION
Every cut needs a written rule and a named decider. That is what makes a selection defensible.
5B / 10
Submitted
Eligibility screen
Reviewer scoring
Reconciliation
Judges decide
Verify and notify
085 ESTIMATE
130–160
125–155 at 96%
~465 reviews
Ranked list
40 winners
40 notified
WHAT HAPPENS
Platform closes; late and failed uploads handled by the published rule
Human plus light AI checks on self-reported items; above 300 entries, revisit with the client
[3] reviewers per entry score each criterion 0–6 against written statements
Scores 2+ points apart discussed, not averaged; comments kept for teams
Minimum score, cap on winners, tie-breakers, published policy factors
Eligibility re-checked, payee details collected, private notice, then announcement
WHO DECIDES
Rules decide; APM applies
FedTech screens; client confirms any disqualification
Reviewers score; they do not select
FedTech moderates; review lead signs
The agency's appointed judges
PM, with client sign-off on the payee list
RECORD KEPT
Submission log with timestamps
Screening log, reason per exclusion
Scores and comments
Reconciliation notes
Signed decision memo
Confirmed payee list
045 LESSON
A third arrived on the last day
89 of 93 eligible; 4 out on citizenship or location
18 of 49 reviews in at the soft deadline
AI-use policy set mid-review; set it first
Name the judges and check dates at kickoff
Feedback to teams after the announcement
THE NUMBER THAT DECIDES IT
Reviewers needed = submissions × reviewers per entry ÷ cap per reviewer. 155 × 3 ÷ 12 ≈ 39, so recruit about 50 to cover conflicts and drop-outs.
ASK THE CLIENT
Who are the appointed judges, and are they free on the judging dates? What minimum score and cap on winners do you want?
Notes: Extends slide 5 into judging. The 085 estimate carries from slide 5A: 130 to 160 submitted, 125 to 155 eligible at the 045 rate of 96%, and 40 Phase I winners from a pool about 4x the winners. Review load is illustrative: about 155 eligible entries x 3 reviewers = about 465 reviews; at a cap of 12 per reviewer that is about 39 reviewers, so recruit about 50. Replace the reviewers per entry and cap with the client's choice. Scoring 0 to 6 against written statements follows DOE LASSO 3.7.1 to 3.7.2; minimum score, cap and tie-breakers follow NASA Cube Quest and DARPA SubT (see slide 7). Judges are appointed by the agency under 15 U.S.C. 3719(k). 045 evidence: 89 of 93 eligible; 18 of 49 reviews in at the August 25 soft deadline with six reviewers replaced; AI-use guidance written mid-review. Sources: TRDNT weekly syncs July 21 to September 1, 2026.