## Slide 1: From problem to adoption
An outcome-first approach to open innovation challenges and prizes
Discussion document · Prepared for [Client] · October 2026
Notes: Purpose of the meeting: share how we approach open innovation challenges, test where you are on the journey, and agree a first step. Keep this to a conversation — the framework is a tool for deciding, not a sales pitch for a prize.

## Slide 2: Well-designed challenges reach solvers that your own networks never would
10×
Leverage on the purse
26 teams spent more than $100M competing for the $10M Ansari XPRIZE.
Outsiders
Distant-field solvers win more often
Across 166 science challenges and 12,000+ solvers, the further a solver's field was from the problem's, the likelier they were to solve it.
$194M
Federal prize purses
251 US federal prize competitions ran in FY2021–22. Prizes are now a mainstream tool, not an experiment.
Pay for
results, not proposals
A prize pays only when the outcome is achieved, shifting technical risk to the teams that choose to compete.
Sources: XPRIZE / Ansari X Prize history; Jeppesen & Lakhani, Organization Science (2010); OSTP, Implementation of Federal Prize Authority FY2021–22 (2024).
Notes: Lead with the distant-solver finding: it is the most counterintuitive and the most important for design. It is why we spend so much effort writing the problem so outsiders recognize it.

## Slide 3: Disappointing challenges usually fail before launch or after the award, not during the competition
Before launch
Most failures start here
Wrong problem. The answer is obvious or can be bought, or the problem is too vague or confidential to publish.
No owner. The problem belongs to someone who is not in the room and will not use the result.
Mis-sized incentives. The purse is too small for the effort asked, or the IP terms scare off the best solvers.
Under-budgeted. In disclosed federal cases, running a small prize cost 1.7× to 11× its purse.
During
Usually recoverable
Thin participation. Outreach stays inside the obvious field.
Contested judging. Criteria are unmeasurable or drift.
After the award
The most expensive failure
Solution orphans. 81% of corporate innovation programs converted fewer than 1 in 4 startup pilots into commercial deals.
Late procurement. There is no contract or pilot route, so winners wait for months.
Not invented here. Internal experts treat outside answers as a threat.
Sources: Nextgov (2012) on White House-disclosed prize administration costs; 500 Startups survey of 100+ corporate innovation programs, via Fortune (2017); Lifshitz-Assaf, NYU Stern, on NASA open innovation.
Notes: The message: the competition itself is the easy part. Our framework puts most of the effort into the two places where challenges actually fail — the front end (problem and design) and the back end (adoption).

## Slide 4: Six principles that the best practitioners agree on
1
Start from the outcome, not the prize
Decide whether you need ideas, prototypes, a market, awareness, action or transformation. Then design backward from it.
Deloitte (2014); NASA outcome-driven open innovation
2
Treat a challenge as one tool among several
Test it against scouting, contracts, grants and internal R&D. If the answer can be bought, buy it.
OSTP; XPRIZE "can a prize help?"; Boudreau & Lakhani (2013)
3
Treat the problem statement as the product
Define the need rigorously, then strip out jargon so solvers from distant fields recognize their expertise.
Spradlin, HBR (2012); Jeppesen & Lakhani (2010)
4
Front-load the effort
The best prizes spend months on landscape and design with experts and likely competitors before announcing a purse.
McKinsey (2009); XPRIZE prize design
5
Design the ending first
Fix the landing zone (adoption owner, budget, pilot or procurement route) before launch, not after the award.
Challenge.gov "Transition"; MITRE on prize-to-procurement
6
Leave a capability, not an event
The network, templates and internal champions should outlast the challenge and feed the next one.
DOE American-Made; NASA CoECI; Nesta
Notes: These six principles are distilled from McKinsey, Deloitte, the Challenge.gov toolkit, XPRIZE, Nesta/Challenge Works, InnoCentive/Wazoku and Harvard LISH research. Every phase of the journey enforces at least one of them.

## Slide 5: The Challenge Journey: six phases, each ending in a decision gate
BEFORE LAUNCH
IN MARKET
AFTER AWARD
1
Commit
What outcome do we need, and are we ready to act on the answer?
2–4 weeks
Ready to commit
2
Frame
Which problem, stated so the right outsiders recognize it?
3–6 weeks
Problem approved
3
Design
Which mechanism, rules and incentives — and where will the winner land?
4–8 weeks
Design signed off
4
Mobilize
Are the right solvers, including unexpected ones, competing?
1–12 months
Participation check
5
Select
Can we pick winners fairly, defensibly and on evidence?
2–6 weeks
Awards approved
6
Adopt
Does the solution get used, and does the capability stay?
3–24 months
Scale, iterate or stop
Throughout: build a lasting capability
Named sponsor and problem owner · stakeholder governance and gates · solver and partner network · reusable rules, templates and metrics · problem pipeline for the next challenge
Notes: This is the one-page view. Walk it left to right. Stress three things: (1) half the phases happen before anything is announced; (2) every phase ends in an explicit decision, including the decision not to proceed; (3) the bottom band — the capability — is what makes the second challenge cheaper and better than the first. Durations are typical ranges, not commitments.

## Slide 6: The first decision: is a challenge the right tool for this problem at all?
Q1
Does a workable solution probably already exist somewhere?
YES
Technology scouting or a targeted partner search
License or partner for it, don't reinvent it
Q2
Is the work well defined, with known skills required?
YES
Crowd labor market or invited contest
Many entrants lower effort per entrant on well-specified tasks
Q3
Must contributions build on one another?
YES
Collaborative community
Open-source-style cumulative work
Q4
Is it novel and uncertain, with measurable success?
YES
Open challenge or prize
Many independent attempts surface extreme-value solutions
If the answer to every question is no: use a grant, a contract or internal R&D. Prizes tend to suit well-defined leaps better than open-ended basic research.
Sources: Boudreau & Lakhani, HBR (2013); Boudreau, Lacetera & Lakhani, Management Science (2011); Pisano & Verganti, HBR (2008); InnoCentive/Wazoku challenge types.
Notes: Ask the questions in order — they are a sieve. Most first-time sponsors assume they need a prize; a meaningful share actually need scouting. Saying so builds trust.

## Slide 7: 1 · Commit: agree the outcome and confirm the organization can act on the answer
1 Commit
2 Frame
3 Design
4 Mobilize
5 Select
6 Adopt
“What outcome do we need, and are we ready to act on the answer?”
What we do together
Choose the outcome: new ideas, prototypes and pilots, a market, awareness, action or transformation.
Assess readiness on eight dimensions, from sponsor and owner to budget, IP, capacity to absorb a solution and adoption route.
Name an executive sponsor and a problem owner who will personally use the result.
Test the alternatives: scouting, grant, contract or internal R&D.
What you get
Outcome statement
Readiness scorecard with gaps and fixes
Sponsor and owner commitments
Go / no-go recommendation
Gate: Ready to commit
Problem owner named and engaged
Funding covers operations and transition, not just the purse
No red flags on ownership, capacity or adoption route
Typical duration: 2–4 weeks
Best-practice anchors: Deloitte, Craft of Incentive Prize Design (2014); Challenge.gov toolkit "Prepare"; NASA@Work requires owners to own the problem.

## Slide 8: 2 · Frame: find the right problem and state it so unexpected solvers recognize it
1 Commit
2 Frame
3 Design
4 Mobilize
5 Select
6 Adopt
“Which problem, stated so the right outsiders recognize it?”
What we do together
Discover: interview owners and mine roadmaps for a long list of gaps.
Prioritize: score each candidate on challenge fit and select one to three.
Define: establish and justify the need, set its context, then write the statement.
Abstract: remove jargon and confidential detail, and break big problems into solvable modules.
Test the draft with a few likely solvers before anything is published.
What you get
Problem long list with fit scores
Problem statement: internal and solver-facing versions
Measurable success criteria
Landscape of what has been tried
Gate: Problem approved
Owner signs off the statement
Success can be measured and judged objectively
Publishable without confidential detail; not purchasable today
Typical duration: 3–6 weeks
Best-practice anchors: Spradlin, "Are You Solving the Right Problem?" HBR (2012); Jeppesen & Lakhani (2010); NASA on problem decomposition.

## Slide 9: 3 · Design: build the challenge backward from the outcome and fix where the winner will land
1 Commit
2 Frame
3 Design
4 Mobilize
5 Select
6 Adopt
“Which mechanism, rules and incentives — and where will the winner land?”
What we do together
Structure: single or staged (ideas, then design, then prototype, then pilot), with milestone awards.
Incentives: a purse sized to solver effort and follow-on value, plus test access, data, mentoring and buyers.
Rules: eligibility, IP and data terms that enable the adoption route.
Judging: measurable criteria, a rubric, the panel and conflict checks.
Landing zone: an adoption owner, a budget, and a pilot, procurement or license route.
What you get
Challenge design brief
Rules, terms and IP model
Judging plan and rubric
Landing-zone plan
Full-lifecycle budget and outreach plan
Gate: Design signed off
Sponsor, legal and procurement sign off
Transition is funded
A team can read the rules and know exactly what wins
Typical duration: 4–8 weeks
Best-practice anchors: Deloitte's five design elements; XPRIZE "audacious but achievable"; MITRE, From Prize Competitions to Procurement.

## Slide 10: 4 · Mobilize: recruit beyond the usual suspects and help teams reach a credible entry
1 Commit
2 Frame
3 Design
4 Mobilize
5 Select
6 Adopt
“Are the right solvers, including unexpected ones, competing?”
What we do together
Recruit across disciplines, not just in the obvious field. Outsiders win disproportionately.
Enlist multipliers: universities, professional societies, accelerators, labs and diaspora networks.
Lower early barriers: a cheap first round, office hours, Q&A and team matching.
Steer with data: track registrations and discipline mix weekly and adjust outreach mid-course.
What you get
Launch and outreach campaign
Partner and multiplier network
Solver support program
Participation dashboard
Gate: Participation check
Enough qualified entries to judge
Spread across distinct disciplines
If not: extend, adjust outreach, or re-scope
Typical duration: 1–12 months
Best-practice anchors: DOE American-Made Challenges "Power Connectors"; Boudreau, Lacetera & Lakhani (2011); Deloitte on non-cash motivators.

## Slide 11: 5 · Select: judge on evidence, defensibly, with the people who will adopt the result
1 Commit
2 Frame
3 Design
4 Mobilize
5 Select
6 Adopt
“Can we pick winners fairly, defensibly and on evidence?”
What we do together
Build the panel: balanced, conflict-screened and calibrated on the rubric before scoring.
Triage in stages: eligibility screen, then blind expert review, then finalist testing.
Reconcile divergent scores in discussion rather than averaging them away.
Verify winners: eligibility, compliance and reproducible results.
Seat the problem owner on the panel. Adoption starts here.
What you get
Scored, documented decisions
Verified winners
Award announcement and recognition
Audit-ready decision record
Gate: Awards approved
Results verified and reproducible
Decision record defensible to any entrant
Sponsor approves awards
Typical duration: 2–6 weeks
Best-practice anchors: Challenge.gov toolkit "Conduct" and "Award"; XPRIZE objective testing; 15 U.S.C. §3719 judging requirements (federal).

## Slide 12: 6 · Adopt: move winners into use and keep the network working
1 Commit
2 Frame
3 Design
4 Mobilize
5 Select
6 Adopt
“Does the solution get used, and does the capability stay?”
What we do together
Activate the landing zone: the pre-agreed pilot, contract, license or investment.
Showcase winners to buyers, investors and follow-on funders.
Hand off the network: solvers, experts and partners stay reachable.
Measure impact at 12, 24 and 36 months. Most impact arrives after the prize closes.
Feed the pipeline: lessons and the next problem go into the next challenge.
What you get
Pilot or contract under way
Network handoff package
Impact report
Lessons learned and next-problem pipeline
Gate: Scale, iterate or stop
Scale: evidence supports wider use
Iterate: a promising gap remains
Stop: record and share what was learned
Typical duration: 3–24 months
Best-practice anchors: Challenge.gov toolkit "Transition"; Deloitte "legacy"; Nesta/Challenge Works; Unilever Foundry funded pilots.

## Slide 13: The goal is a repeatable capability; the first challenge is how you start building it
First challenge
Learn by doing
One well-framed problem with an engaged owner
Templates and rules drafted for reuse
Internal champions identified and celebrated
Repeatable practice
Make the second one cheaper
A problem pipeline with intake criteria
Pre-agreed legal, IP and procurement templates
A standing solver and partner network
Standing program
Open innovation as a normal tool
A center of excellence that brokers methods
Pre-competed vehicles to buy challenge services fast
Portfolio review and an outcomes dashboard
Culture is the binding constraint. In NASA's experience, external solutions were adopted only where internal experts came to see themselves as "solution seekers" as well as problem solvers. Involve them as co-designers and judges, not bystanders.
Examples: NASA CoECI and the NOIS contract vehicles; DOE American-Made Challenges; P&G Connect + Develop. Culture finding: Lifshitz-Assaf, NYU Stern study of NASA R&D.

## Slide 14: A first challenge typically takes 5–18 months from commitment to award; adoption continues beyond that
M0
M3
M6
M9
M12
M15
M18
1 Commit
2–4 weeks
2 Frame
3–6 weeks
3 Design
4–8 weeks
4 Mobilize
1–12 months
5 Select
2–6 weeks
6 Adopt
3–24 months
Before launch: about 2–4 months
In market: varies with challenge type
After award: ongoing
Illustrative mid-range plan. Ideation challenges can run in weeks; hardware prizes with physical testing can run for years. Durations draw on Challenge.gov, Nesta and DOE American-Made practice.

## Slide 15: Success depends on a few named people on your side; we bring the rest
From you
Executive sponsor
Owns the outcome and budget; chairs the gates; attends the award.
Problem owner
Signs the problem statement, sits on the panel and adopts the result.
Legal and IP
Confirms authority, IP model and terms early, not at launch.
Procurement
Designs the pilot or contract route before launch.
Finance
Funds the purse, operations and transition as one budget.
Communications
Owns brand and story; amplifies outreach.
From us, end to end
Readiness and problem-discovery facilitation
Problem framing and abstraction
Challenge design, rules, judging and budget
Platform, outreach and solver support
Judging operations and winner verification
Transition support, network handoff and impact measurement
Notes: Push gently on the problem owner and procurement roles. These are the two most commonly missing, and the two most predictive of whether a winner is ever used.

## Slide 16: Proposed next step: a six-week Commit-and-Frame sprint ending in a go / no-go
1
Weeks 1–2
Readiness
Five to eight stakeholder interviews; readiness scorecard; outcome statement draft
2
Weeks 2–3
Discovery workshop
Half-day session to build and score a long list of candidate problems
3
Weeks 4–5
Frame
Problem statements for the top one to three; landscape scan; solver-pool check
4
Week 6
Decision
Go / no-go, recommended mechanism and an outline design brief
Decisions we would like from today
Who is the executive sponsor, and who are the candidate problem owners?
Which five to eight people should we interview in weeks 1–2?
A date for the half-day discovery workshop
Any constraints we should know now: authority, IP, procurement, timing

## Slide 17: Sources
Boudreau, K. & Lakhani, K. (2013). Using the Crowd as an Innovation Partner. Harvard Business Review.
Boudreau, K., Lacetera, N. & Lakhani, K. (2011). Incentives and Problem Uncertainty in Innovation Contests. Management Science.
Challenge.gov / GSA. Prize and Challenge Toolkit (Prepare, Develop, Conduct, Award, Transition).
Deloitte GovLab (2014). The Craft of Incentive Prize Design: Lessons from the Public Sector.
Jeppesen, L. B. & Lakhani, K. (2010). Marginality and Problem-Solving Effectiveness in Broadcast Search. Organization Science.
Lifshitz-Assaf, H. (2018). Dismantling Knowledge Boundaries at NASA. Administrative Science Quarterly.
McKinsey & Company (2009). And the Winner Is…: Capturing the Promise of Philanthropic Prizes.
MITRE. From Incentive Prize and Challenge Competitions to Procurement.
Nesta / Challenge Works. Challenge Prizes: A Practice Guide.
Nextgov (2012). White House discloses administrative costs for innovation contests.
OSTP (2024). Implementation of Federal Prize and Citizen Science Authority, FY2021–22.
Pisano, G. & Verganti, R. (2008). Which Kind of Collaboration Is Right for You? Harvard Business Review.
Spradlin, D. (2012). Are You Solving the Right Problem? Harvard Business Review.
US DOE / NREL. American-Made Challenges program and Power Connectors.
XPRIZE Foundation. Prize design process; Ansari X Prize history.
500 Startups survey of corporate innovation programs, reported in Fortune (2017).