## Slide 1: Challenge Journey Playbook
Internal methodology, tools and workshop guides for client open innovation challenges and prizes
Practitioner use · Version 1.0 · October 2026

## Slide 2: How to use this playbook
1
The framework
Six phases, their gates and the evidence behind them. Use it to orient the team and the client.
Slides 3–6
2
The tools
Ten working tools, from readiness scorecard to landing-zone plan, plus KPIs and a risk register. Each maps to a phase.
Slides 7–19
3
The workshops
Agendas for the first client meeting and the half-day problem-discovery workshop, plus a question bank.
Slides 20–23
4
The evidence
Claims we cite, with sources and a flag where the figure must be checked before external use.
Slides 24–25
Ground rule: a gate is a real decision. Recommending "not now" or "use scouting instead" is a good outcome, not a lost sale.

## Slide 3: The Challenge Journey on one page
BEFORE LAUNCH
IN MARKET
AFTER AWARD
1
Commit
What outcome do we need, and are we ready to act on the answer?
2–4 weeks
Ready to commit
2
Frame
Which problem, stated so the right outsiders recognize it?
3–6 weeks
Problem approved
3
Design
Which mechanism, rules and incentives — and where will the winner land?
4–8 weeks
Design signed off
4
Mobilize
Are the right solvers, including unexpected ones, competing?
1–12 months
Participation check
5
Select
Can we pick winners fairly, defensibly and on evidence?
2–6 weeks
Awards approved
6
Adopt
Does the solution get used, and does the capability stay?
3–24 months
Scale, iterate or stop
Throughout: build a lasting capability
Named sponsor and problem owner · stakeholder governance and gates · solver and partner network · reusable rules, templates and metrics · problem pipeline for the next challenge

## Slide 4: Each phase maps onto the established models, so clients can trace our method to recognized practice
Our phase | Challenge.gov / GSA | Deloitte (2014) | Nesta / Challenge Works | XPRIZE | InnoCentive / Wazoku
1 Commit | Prepare: goals, fit, authority, budget | Choose among six outcomes | Discover | "Can a prize help?" | Establish and justify the need
2 Frame | Prepare: define the problem | — | Define | Landscape analysis; prizeability | Contextualize; write; abstract
3 Design | Develop: structure, rules, judging, metrics | Five design elements | Design | Prize direction, then design | Challenge type and award
4 Mobilize | Conduct: communications, submissions | Implementation | Deliver: team support | Registration and team support | Post to the solver crowd
5 Select | Conduct: judging, verification; Award | Evaluation; Award | Deliver: judging | Semifinals, finals, testing | Seeker evaluation; award
6 Adopt | Transition: document, engage, manage solutions | Legacy | Impact (after prize) | Impact strategy | Seeker implements
Throughout | Build the team; share best practice | Resources; communications | Ecosystem impact | Operational plan | Challenge-driven enterprise
Sources: GSA Prize and Challenge Toolkit; Deloitte, The Craft of Incentive Prize Design (2014); Nesta/Challenge Works Practice Guide; XPRIZE prize design; Spradlin, HBR (2012). Labels paraphrased from search summaries; confirm against primary documents.

## Slide 5: Engagement model: what each phase demands of us and of the client
Phase | Typical duration | Our core activities | Client time required | Key deliverables
1 Commit | 2–4 weeks | Stakeholder interviews; readiness scoring; outcome framing; alternatives check | Sponsor 2 hrs; 5–8 interviewees 1 hr each | Outcome statement; readiness scorecard; go/no-go
2 Frame | 3–6 weeks | Discovery workshop; fit scoring; problem statements; abstraction; landscape scan; solver test | Owners: workshop + 2–3 working sessions | Long list; 1–3 problem statements; success criteria
3 Design | 4–8 weeks | Mechanism and structure; incentives; rules and IP; judging plan; landing zone; budget; outreach plan | Legal, procurement, finance reviews | Design brief; rules; judging plan; landing-zone plan; budget
4 Mobilize | 1–12 months | Launch; outreach; partner network; solver support; participation tracking | Comms amplification; owner Q&A | Campaign; partner network; dashboard
5 Select | 2–6 weeks | Panel recruitment and calibration; staged triage; reconciliation; verification | Judges; owner on panel; sponsor approval | Decision record; verified winners; award event
6 Adopt | 3–24 months | Landing-zone activation; showcases; network handoff; impact measurement | Owner and procurement lead adoption | Pilot or contract; handoff; impact report
Durations are planning ranges synthesized from Challenge.gov, Nesta and DOE American-Made practice; calibrate per engagement. Client time estimates are our planning assumptions.

## Slide 6: Gate criteria: what must be true to move to the next phase
Gate | Decision | Must be true | Decides
1 Ready to commit | Proceed, fix gaps first, or not now | Named problem owner; budget covers operations and transition; no red score on owner, absorptive capacity or adoption route; a challenge beats the alternatives | Executive sponsor
2 Problem approved | Which problem(s) go to design | Owner signs the statement; success measurable; publishable without confidential detail; not purchasable today; plausible solver pool exists | Sponsor + problem owner
3 Design signed off | Launch or revise | Rules unambiguous (a team knows what wins); IP model fits the adoption route; judging plan approved; transition funded; legal and procurement sign off | Steering group
4 Participation check | Continue, extend, re-scope | Qualified entries meet the target; entrants span distinct disciplines; no unresolved rule disputes | Challenge manager + owner
5 Awards approved | Confirm winners | Scores reconciled and documented; winners verified (eligibility, compliance, reproducibility); decision record defensible | Sponsor (or federal judges)
6 Scale, iterate or stop | What happens to the result | Pilot evidence reviewed against success criteria; next-step budget and owner identified; lessons captured | Sponsor + owner

## Slide 7: The toolkit
Ten working tools. Each one produces a client-ready deliverable and feeds a gate.

## Slide 8: Tool 1 · Readiness scorecard (Commit): score eight dimensions from 1 to 5
# | Dimension | What a 5 looks like | Red flag (score 1–2)
1 | Executive sponsor | Named senior owner with budget authority who will attend the award | "The innovation team will handle it"
2 | Problem owner ★ | Owner who will personally use the result and sit on the panel | "We're solving this for another department"
3 | Funding | Purse, operations and transition budgeted together | Only the purse is funded
4 | Legal and IP posture | Authority confirmed; IP model agreed in principle | Legal first engaged at rules drafting
5 | Absorptive capacity ★ | People, test facilities and budget to evaluate and integrate a solution | No one has time to test the winner
6 | Adoption pathway ★ | Pilot, procurement or license route identified | "We'll work out next steps after the award"
7 | Cultural openness | Experts see outside solutions as wins; some prior open innovation | A challenge is seen as a verdict on internal staff
8 | Measurement | Baseline and target metrics defined | Success means "good press"
Suggested decision rule
Proceed: 28–40, and no ★ item below 3
Fix first: 20–27, or any ★ item below 3
Not now: below 20. Offer scouting or an internal challenge to build familiarity
★ Low scores on these three predict "solution orphans": winners nobody adopts. Thresholds are our heuristic; recalibrate after the first few uses.
Synthesized from the IBM/APQC ecosystem innovation maturity model, Mind the Bridge Open Innovation Readiness Index, NASA@Work owner rules and Cohen & Levinthal on absorptive capacity.

## Slide 9: Tool 2 · Outcome selector (Commit): the outcome you choose drives every design choice
Outcome you need | Design implications | Example metrics
Develop solutions |  | 
Attract new ideas | Low entry barrier; short window; small guaranteed awards; broad, multidisciplinary outreach | Number of novel ideas; solver diversity; share new to the sponsor
Build prototypes and launch pilots | Staged structure; milestone awards; test facilities; reduction-to-practice evidence; pilot partner lined up | Performance against target; pilots launched
Stimulate markets | Large purse or purchase commitment; clear performance threshold; investor and buyer engagement | Entrants; private investment; price or cost change
Engage people |  | 
Raise awareness | Public-facing format; storytelling; media-worthy finish | Reach; engagement; sentiment
Mobilize action | Participation prize; community tools; low-cost entry | Actions taken; participants retained
Inspire transformation | Long horizon; network-building; legacy funding | Policy or practice change; network ties formed
Outcome typology: Deloitte, The Craft of Incentive Prize Design (2014). Prize archetypes for cross-reference: McKinsey (2009): point-solution, market-stimulation, participation, exemplar, exposition, network.

## Slide 10: Tool 3 · Challenge-fit scorecard (Frame): score each candidate problem out of 70
Criterion | Weight | Score 1–5 | Stop if
Important and widely recognized as a problem | ×2 |  | 
Solution not obvious and cannot be bought off the shelf ★ | ×2 |  | Purchasable: procure or scout
Outsiders could plausibly contribute; a solver pool exists | ×2 |  | 
Success measurable and objectively judgeable ★ | ×2 |  | Not measurable: reframe
Can be stated without confidential context | ×1 |  | 
IP and data shareable on acceptable terms | ×1 |  | 
Owner and adoption path exist ★ | ×2 |  | No owner: park it
Solvable at reasonable cost and time relative to the incentive | ×1 |  | 
A challenge beats grants, contracts and internal R&D here | ×1 |  | 
Total (maximum 70) |  |  | 
Reading the score
50+: strong candidate
35–49: reframe or decompose, then rescore
Below 35: use another tool
Any ★ scored 1: stop, whatever the total
Run it as dot-voting in the discovery workshop, then score the top candidates properly with the owner.
Criteria compiled from Nesta ("When is your problem a challenge?"), the Challenge.gov toolkit, McKinsey's conditions for incentive prizes and XPRIZE prizeability tests. Weights and thresholds are our heuristic.

## Slide 11: Tool 4 · Problem-statement canvas (Frame): define rigorously, then abstract for outsiders
1 Need
Why solve this now? What happens if we don't?
2 Justification
Strategic fit; value of a solution; who benefits
3 Context
What has been tried, by us and others; why it fell short; constraints
4 How might we…
One sentence that implies a solution is possible without prescribing it
5 Success criteria
Measurable thresholds a judge can verify; what must and must not be true
6 Out of scope
Approaches, technologies or markets we exclude, and why
7 Solver-facing version
Rewrite without jargon or confidential detail, for a capable person in a distant field
8 IP and data
What solvers keep, what we need, which data we can share
9 Owner and landing zone
Who adopts the result, through which route, with what budget
Boxes 1–3 and 5 follow Spradlin's four steps (HBR, 2012); box 4 is IDEO's "How might we"; box 7 applies the abstraction evidence of Jeppesen & Lakhani (2010). Balance abstraction against fit: too abstract draws irrelevant entries (Wazoku's "Goldilocks" point).

## Slide 12: Tool 5 · Mechanism selector (Design): match the open-innovation mechanism to the problem
Mechanism | Use when | Typical incentive | Reference models
Technology scouting / partner search | A solution probably exists; you want a license or partner | Contract or license | NineSigma, yet2, Innoget, eRFP
Ideation challenge | You need many early ideas fast | Small, often guaranteed awards | InnoCentive ideation; OpenIDEO
Theoretical / design challenge | You need a detailed, testable design | Mid-size award; IP often transferred | InnoCentive Theoretical
Prototype / reduction-to-practice prize | You need working evidence against a threshold | Large, staged purse plus test access | XPRIZE; NASA Centennial; InnoCentive RTP
Data / algorithm contest | Performance can be scored on held-out data | Leaderboard purse | Kaggle; NASA Tournament Lab
Crowd labor market / task contests | Work is well-defined with known skills | Pay per accepted output | Topcoder
Collaborative community | Contributions must build on one another | Recognition, access, shared use | Open source
Market-stimulation prize | You want to drive down cost or prove demand | Large purse or purchase commitment | McKinsey market-stimulation archetype
Boudreau & Lakhani, HBR (2013); Boudreau, Lacetera & Lakhani (2011): open wide for uncertain problems, limit entry for well-specified ones; InnoCentive/Wazoku challenge types; Pisano & Verganti (2008).

## Slide 13: Tool 6 · Design checklist (Design): decide all five elements together, not in sequence
Structure
Single or multi-stage?
Milestone or progress awards?
Eligibility and team rules
Timeline and stage gates
Motivators
Purse and its split across stages
Test access, data, mentoring
Access to buyers and investors
Recognition and validation
Evaluation
Criteria derived from the outcome
Objective test or rubric
Panel and conflict checks
Winner verification
Resources
Platform and datasets
Test facilities and protocols
Partners and multipliers
Staffing and budget
Communications
Brand and story
Outreach channels by discipline
Community management
Award moment and media
IP model spectrum: the heavier the encumbrance, the smaller and more skewed the solver pool
Solvers keep IP
License option or right of first negotiation
Open-source requirement
Full assignment for the award
Five elements: Deloitte (2014). IP spectrum: Frangione (XPRIZE) Senate testimony; InnoCentive terms. Federal: 15 U.S.C. §3719 bars taking participant IP without written consent (confirm with counsel).

## Slide 14: Tool 7 · Purse and budget worksheet (Design): size the purse to the solver, budget the whole lifecycle
Five lenses for the purse
Cost to solve: the expected prize plus non-cash value must justify the effort of the target solver.
Follow-on value: a weak follow-on market needs a bigger purse or more non-cash value.
Value to sponsor: the purse should be a fraction of the cost or time it saves.
Signal: the size of the purse tells solvers how much the problem matters.
Staging: spread the purse across stages to fund more early teams and keep option value.
Federal average ≈ $775K per competition (FY21–22: $194.4M across 251)
Federal: purses over $1M need agency-head approval; over $50M, 30 days' notice to Congress
Kaggle ≈ $10K–$250K; InnoCentive-type ≈ $5K–$100K+ (verify)
Lifecycle budget line | Often missed?
Design and problem framing | 
Legal, rules and IP | 
Platform and data | 
Outreach and partner network | 
Solver support (mentoring, vouchers, test access) | Often
Judging and testing (costly for hardware) | Often
Purse | 
Transition (pilot, contract vehicle, adoption) | Most often
Evaluation and reporting | Often
Do not quote operations as a fixed ratio of the purse. In disclosed small federal prizes, administration ran 1.7× to 11× the purse; the ratio falls as purses grow.
Sources: OSTP FY2021–22 report; 15 U.S.C. §3719; Nextgov (2012); Kay, IBM Center for the Business of Government (2011); McKinsey (2009).

## Slide 15: Tool 8 · Governance and RACI (all phases): who decides what
Activity | Exec sponsor | Problem owner | Our team | Legal | Procurement | Comms | Judges
Readiness go / no-go | A | C | R | C | C | – | –
Problem selection and statement | A | R | R (facilitate) | I | I | – | –
Rules, eligibility and IP terms | I | C | R | A | C | I | I
Purse and lifecycle budget | A | C | R | I | C | – | –
Outreach and solver support | I | C | A / R | – | – | R | –
Judging process | I | C | R | C | – | – | –
Award decisions | A | C | C | C | – | I | R
Transition vehicle | A | R | C | C | R | – | –
Impact measurement | A | C | R | – | – | I | –
Steering group
Chaired by the sponsor, with the problem owner, legal, procurement, finance and communications. It meets at every gate.
Federal note: under 15 U.S.C. §3719 judges must be conflict-free, panels are exempt from FACA, and agencies may contract a private entity to administer the prize. Federal judges make award determinations.
R = responsible, A = accountable, C = consulted, I = informed. Adapted from Wazoku/Planview platform roles and NC3Rs CRACK IT sponsor roles. Bring procurement in during Commit, not after the award.

## Slide 16: Tool 9 · Judging design (Design to Select): defensible decisions in seven steps
1
Criteria
Derived from the outcome; published in advance; measurable
2
Panel
Balanced expertise; the problem owner included; conflicts screened
3
Calibrate
Train on the rubric; score sample entries together
4
Triage
Eligibility screen, then blind expert review, then finalists
5
Test
Objective tests or held-out data wherever possible
6
Reconcile
Discuss divergent scores; never average them away
7
Verify and record
Eligibility, compliance, reproducibility; audit trail
Practitioner notes
"You get what you incentivize": any criterion that can be gamed will be. Pressure-test the rubric with a mock entry.
Where reviewers in different disciplines score the same entry, keep the tracks separate and reconcile in a moderated session. The split is often the most important signal.
Seating the problem owner on the panel is also the first step toward adoption.
Challenge.gov toolkit ("Conduct": manage judging, verify winners); XPRIZE objective testing; Frangione, Senate testimony.

## Slide 17: Tool 10 · Landing-zone plan (Design to Adopt): decide where the winner lands before launch
Questions to answer before launch
Who adopts the result, and have they agreed to?
Through which route: pilot, procurement, license, investment or a follow-on challenge?
What budget, and when is it available?
Do the IP and data terms allow that route?
What does a winner get beyond cash: a pilot, a buyer meeting, validation data?
What does success look like at 12, 24 and 36 months?
Who holds the solver and expert network after handoff?
Government routes
Follow-on contract justified by the competition
Competition results used as the competitive evaluation
Other Transaction (OTA) follow-on production
SBIR/STTR on-ramp for winning teams
Vouchers for national-lab access (DOE model)
Corporate routes
Pre-committed investment pool (GE ecomagination)
Funded pilots on a standard contract (Unilever Foundry)
Royalty or license (LEGO Ideas)
Proof-of-concept gates with follow-on funding (Shell GameChanger)
MITRE, From Incentive Prize and Challenge Competitions to Procurement; DOE American-Made Challenges; corporate examples from secondary sources (see evidence bank).

## Slide 18: Measuring success: five levels of KPIs, tracked from launch through 36 months
Level | Indicators | When
Activity | Registrations; submissions; disciplines and geographies represented; share new to the sponsor; stage-pass rates | During Mobilize
Output | Solutions meeting the threshold; performance against baseline; judge scores | At Select
Efficiency | Cost per viable solution against the internal baseline; time to solution; solver investment as a multiple of the purse | At award and close
Outcome | Share of winners piloted; share adopted or contracted within 12–24 months; follow-on funding raised; licenses | 12–36 months
Capability | Repeat problem owners; size of the problem pipeline; time from intake to launch; internal attitude survey | Annually
Synthesized from OSTP prize reporting, Nesta impact evaluation and DOE American-Made practice. Nesta: most impact arrives after the prize closes, so budget the 12–36 month follow-up.

## Slide 19: Risk register: the ten most common failure modes, their early warnings and mitigations
Failure mode | Early warning | Mitigation | Phase
Wrong problem | Solution is obvious, purchasable or vague | Fit scorecard; alternatives test | 1–2
Absent owner | Owner skips the interviews | Make a named owner a gate 1 condition | 1
No landing zone | "We'll decide after the award" | Landing-zone plan at gate 3 | 3
Mis-sized purse | Solver test calls it not worth it | Five-lens sizing; staging; non-cash value | 3
Under-budgeted operations | Budget covers the purse only | Lifecycle budget worksheet | 1, 3
Deterrent IP terms | Legal arrives at rules drafting | Legal in Commit; IP model chosen to fit the route | 1, 3
Thin participation | Registrations below target at midpoint | Multidisciplinary outreach; multipliers; extend | 4
Contested judging | Criteria open to interpretation | Calibrated rubric; reconciliation; record | 3, 5
Not invented here | Experts describe the challenge as a threat | Experts as co-designers and judges | All
One-off mindset | No reuse of templates or network | Capability layer; handoff package | 6

## Slide 20: Workshops and facilitation
The first client meeting, the half-day problem-discovery workshop and a question bank.

## Slide 21: First client meeting (60–90 minutes): agenda and facilitator moves
90-min | 60-min | Segment | Facilitator moves | Deck
0–10 | 0–5 | Introductions and objectives | Ask: "What would make this worth your time a year from now?" Note the outcome language they use. | 1
10–25 | 5–15 | Why challenges work and why they fail | Lead with the distant-solver finding; then failure modes. Ask which ones feel familiar. | 2–4
25–45 | 15–30 | The journey and the tool choice | Walk the one-page framework; run the four tool-choice questions against their candidate problem. | 5–6, 13
45–70 | 30–45 | Rapid readiness conversation | Probe the three ★ dimensions: owner, absorptive capacity, adoption route. Score privately afterward. | 7, 15
70–85 | 45–55 | First candidate problems | Capture 3–8 problems verbatim; do not score yet. | —
85–90 | 55–60 | Next steps and decisions | Propose the six-week sprint; confirm sponsor, owners, interviewees and workshop date. | 16
Bring: printed one-page framework, blank readiness scorecard (for your notes only), a list of two or three relevant prize examples from the client's sector.

## Slide 22: Problem-discovery workshop (half-day, Frame): from a long list to one to three challenge-ready problems
Time | Block | Method | Output
Pre-work | Interviews and landscape | Owner interviews; roadmap and gap review; scan of prior challenges in the field | Seed list of 15–30 gaps
0:00–0:20 | Anchor the outcome | Recap Tool 2; agree which outcome this program serves | Agreed outcome
0:20–1:00 | Diverge | Silent writing of pain points as "How might we…"; cluster on a wall | Long list in clusters
1:00–1:40 | Converge | Dot-vote on the ★ fit criteria; discuss outliers | Shortlist of 4–6
1:40–1:55 | Break |  | 
1:55–2:45 | Define | Breakouts fill canvas boxes 1–6 for each shortlisted problem | Draft canvases
2:45–3:20 | Abstract | Rewrite each statement for "a smart engineer in another industry"; swap and critique | Solver-facing drafts
3:20–3:40 | Land it | Canvas box 9: who adopts, which route, what budget | Landing-zone check
3:40–4:00 | Decide | Rank; name owners; agree follow-up scoring and solver tests | Top 1–3 and owners
Participants: sponsor (opening and close), 2–4 problem owners, 2–3 technical experts, one procurement or legal voice. Materials: canvas posters, Tool 3 sheets, dot stickers. Abstraction exercise based on InnoCentive practice.

## Slide 23: Discovery question bank: what to ask in interviews and the first meeting
Outcome
What would success look like in two years?
Are you after a solution, a market, a community, or attention?
What have you tried, and why did it fall short?
Problem
Who else has this problem?
Could you buy the answer today?
How would you know, objectively, that it is solved?
Owner and adoption
Who will use the winning solution day to day?
What happens the week after the award?
Which budget pays for a pilot?
Constraints
What authority lets you award prizes?
What must you own; what can solvers keep?
Can data be shared? Any export controls?
Culture
How will your experts react to an outside winner?
Who internally would champion it?
Has an outside idea ever been adopted here?
Budget and time
Is there funding beyond the purse?
Any fixed dates: fiscal year, events, announcements?
Who signs off spending?

## Slide 24: Evidence bank: claims we use and how confident we are in each
Claim | Source | Status
Distant-field solvers more likely to win (166 challenges, 12,000+ solvers) | Jeppesen & Lakhani, Organization Science (2010) | Peer reviewed
Ansari XPRIZE: 26 teams, >$100M spent for a $10M purse | XPRIZE; Wikipedia | Widely reported
251 federal competitions, $194.4M in purses, FY21–22 | OSTP report (2024) | Government report
More entrants: less effort each, more extreme-value outcomes | Boudreau, Lacetera & Lakhani, Management Science (2011) | Peer reviewed
Small-prize administration 1.7×–11× the purse | Nextgov (2012), White House disclosures | Press, 2012 data
81% convert under 25% of startup pilots into deals | 500 Startups survey via Fortune (2017) | Survey; check wording
NASA scientists adopted external solutions only after identity shift | Lifshitz-Assaf, ASQ (2018) | Peer reviewed
NOIS3: 25 awardees, up to $475M over 10 years | GovConWire (2025) | Trade press; confirm
Unilever Foundry: ~95 pilots, ~45 scaled | FoodNavigator (2016) | Single secondary source
NASA Tournament Lab: ~94% success, 80–99% savings | NASA CoECI presentation | Self-reported
"Operations ≈ 1–2× purse" rule of thumb | None found | Do not use
Research ran through search summaries because the primary PDFs were not reachable from this environment. Check every coral-flagged item against the primary document before using it in a proposal.

## Slide 25: Sources and further reading
Boudreau & Lakhani (2013), Using the Crowd as an Innovation Partner, HBR
Boudreau, Lacetera & Lakhani (2011), Incentives and Problem Uncertainty in Innovation Contests, Management Science
Challenge.gov / GSA, Prize and Challenge Toolkit (2026 edition)
Cohen & Levinthal (1990), Absorptive Capacity, Administrative Science Quarterly
Deloitte GovLab (2014), The Craft of Incentive Prize Design
Frangione, C., XPRIZE testimony to the US Senate Commerce Committee
Jeppesen & Lakhani (2010), Marginality and Problem-Solving Effectiveness in Broadcast Search
Kay, L. (2011), Managing Innovation Prizes in Government, IBM Center for the Business of Government
Lifshitz-Assaf (2018), Dismantling Knowledge Boundaries at NASA, ASQ
McKinsey & Company (2009), And the Winner Is…
MITRE, From Incentive Prize and Challenge Competitions to Procurement
Nesta / Challenge Works, Challenge Prizes: A Practice Guide
NREL, American-Made Solar Prize evaluation (TP-6A50-89607)
OMB M-10-11 (2010), Guidance on the Use of Challenges and Prizes
OSTP (2024), Implementation of Federal Prize and Citizen Science Authority FY2021–22
Pisano & Verganti (2008), Which Kind of Collaboration Is Right for You?, HBR
Spradlin (2012), Are You Solving the Right Problem?, HBR
15 U.S.C. §3719 (America COMPETES Reauthorization Act of 2010, §105)